## Agile Project
Iteration 1, 3 wks 5/6/19-5/24/19 | Iteration 2, 3 wks 6/3/19-6/21/19 | Iteration 3, 3 wks 7/1/19-7/19/19
UC4: Do Four points: 1 priority: 1 dep on: UC1 | UC6: Do Six points: 3 priority: 2 dep on: UC3 | UC8: Do Eight points: 2 priority: 3 dep on: None
UC1: Do One points: 2 priority: 1 dep on: UC2 | UC3: Do Three points: 4 priority: 2 dep: UC7 | UC9: Do Nine points: 3 priority: 4 dep on: UC8
UC2: Do Two points: 1 priority: 1 dep on: None | UC7: Do Seven points: 5 priority: 3 dep on: UC9 | UC5: Do Five points: 5 priority: 4 dep on: UC4
I believe a more significant and qualified staff is needed for this project in order to complete with zero errors.

## Risk Management
Risk | Risk Resolution Measures | Justifications
Personnel shortages is inherently difficult to estimate and schedule | Maintain a healthy, robust, proactive team members to be SME in areas of the project by engaging in planning and estimating. Increasing more collaboration and information sharing throughout the team. | Not having enough staff personnel or team members would hinder the flow of each task schedule, project teams timeline/iteration and milestone to complete the project on schedule. Enough is good enough.
System reliabilities and testing failures | The SAMS system must be able to preform at the highest potential possible for the OIE to facilitate all the students, staff members, and faculty members request. Ensure all steps in functionality and testing is conducted on a regularly basis. | Testing should be conducted after each phase of the project to ensure all checks and balances are reliable and are within specification for the OIE stakeholders to check its operational and functions.
Poor user interface and team productivity | Establishing short iterations, employing the right people, coaching and emphasizing team development will enhance productivity, requirements and sub-requirements on the project. | By given a deadline, people tends to wait until the deadline approaches before starting the work. Agile methods does not specifically address employing the right people, coaching and building team development, however, these are core leadership roles that is applicable to agile and traditional projects.
Web-based application processes and security vulnerabilities is comprised | Having a dedicated product manager to make critical trade off decisions will ensure all phases are properly checked. The main idea is that someone on the team needs to be readily available to answer questions and make accurate decisions in a timely manner on the project. Security must be in place to protect the website from cyber attacks and the privacy of all users. | Traditional projects suffer specification breakdown when no one will own the role and conflicting assumptions or decisions are made. Agile projects have some form of product owner role central to their core team composition to ensure decisions are made in a timely fashion.
System not platform independent, cannot run on different platforms and support a wide varieties of database management systems. | Project managers must have constant involvement with customers, team members and developers, along with OIE staff to facilitate the overall system requirements. | As the project progresses more and more features that were not identified at the beginning of the project emerge that might threaten the estimation and timelines for the entire team and project.